## Sheet1
Date | Summary of Meeting | Members Absent
2016-10-07 | Split deliverable 2 (one due on October 19th) into individual assignments
- Anthony & Haitian = coding structure & efficiency
- Ryan & Aboudi = testing the program and creating test cases
- Matthew = assessment of documentation
- Yusi & Claire = assessment of the user interface
As each person evaluates portion of code, think of potential improvements in the area
2016-10-14 | Brainstormed improvement ideas | Aboudi
Addressed problems with respective areas of the program
Consolidated all information
2016-10-21 | Discussed test cases | Aboudi
- GUI and CSV Test cases
- Plan to add more test cases focused on GUI before deliverable due date
Added a few recommendations to code/algorithm analysis
Compiled deliverables (each individual’s analysis)
Prepared for demo on Monday
Stage 1 Achievements
Half Test Cases
Analyzed Code
Analyzed Algorithms
Analyzed Documentations
Analyzed GUI
Recommendations for Code
Recommendations for GUI
Recommendations for Documentation
Recommendations for Fixing Errors
2016-10-26 | Demo1 Enhanced Requirements Determined | Anthony
Demo1 Enhanced Requirements Tasks Allocated to Specific Group Members
Plans to Create Remainder of Test Cases
Plans to Create Solutions for All Test Cases
2016-10-28 | All Test Cases Done | Aboudi
Half Test Cases Solved
Case Diagrams Done
Original Class Diagrams Done
Work Done on Requirements
Development Plan Completed
2016-10-31 | All Requirements for Demo1 Done | Aboudi
All Test Cases Solved
10/31/2016 (In Class) | Work on Any Incomplete Requirements for Demo1 | Aboudi
Fix Any Test Cases Not Yet Solved for Demo1
Allocate Responsibilities for Demo2
Update Timeline and Agent Task View
Stage 2 Achievements
All Original Code Test Cases + Solutions Complete
Line Graph Added to Project
Navigation of Erroneous Errors Added to Project
Started Test Code for Deliverables
Project Timeline Up To Date
Agent Task Up To Date
Started Work on Saving State
Case Diagram Done
Original Class + Enhanced Class Diagrams Done
11/3/2016 (In Class) | Work on Demo2 Requirements | Aboudi
Work on Stretch Requirements
Begin Work on Package Diagram
Begin Work on Sequence Diagram
2016-11-04 | Meet To Talk About Progress of Demo2 Requirements | Aboudi
Address Any Pain Points
Begin Creation of Test Cases for Phase 2 Requirements
Write Up Design Patterns
Write Up Implementation in C++
2016-11-07 | Talked about deliverable 2 | Ryan
| What we need to fix (mostly test cases) | Aboudi
Need to add more test cases and solve all test cases
Must create and solve test cases for deliverables
Talked about the CSV errors
Problems with array out of bound errors
Problems with MAC? Consider using only Windows OS
2016-11-11 | Test cases created matrix | Aboudi
| Progress on diagrams | Anthony
Save state ideas plan created
- Will begin coding for this week
Will begin second graph coding this week
- Scatterplot
Begin fixing problems with the CSV files
2016-11-18 | Save state completed
CSV reading fixed
Scatterplot graph completed
Package diagram completed
Sequence diagram almost completed
- Waiting on sort code
Sort code will be done by Monday
Still To Do
User proof install
Test cases for deliverables
- Save state
- Navigation of errors
- New sort test code
Test cases in matrix
2016-11-21 | Test cases mostly completed | Aboudi
| Still waiting for Aboudi’s sorting code | Anthony
GUI test cases missing (Aboudi said this was done a long time ago but hasn’t committed to Github)
Compile all documentation into a pdf
Figuring out how to create an install package